## Sheet1
Inpatient Antimicrobial Stewardship Program Implementation Timeline
Created 7/17/17 | This example was created by the Montana ABS Collaborative, using the CDC ASP Core Elements Checklist as a guide. Modify as necessary for your own ASP implementation. Contact Patty Kosednar at pkosednar@mpqhf.org if you would like help or have any questions.
Core Element | High Level Tasks | Sub Tasks | Assigned To | Due Date | Date Completed
N/A | Create ASP team
Choose ASP team leader (Admin)
Choose remaining team members
Accountability |  | Assign a physician leader
Drug Expertise |  | Assign a pharmacist leader
Identify and document roles and responsibilities for each team member
Leadership Support | Create and implement a formal statement of ASP support from leadership
Draft ASP commitment policy
Approve and sign ASP commitment policy
Introduce/communicate ASP policy to entire staff
Tracking | Establish ASP evaluation measure(s) (DOT, cost, volume, etc.)
Choose evaluation measure(s)
Establish baseline data (min 90 days)
Create process for ongoing tracking/monitoring of measure(s)
Tracking | Establish ASP outcome measure(s) (Cdiff, MRSA, etc.)
Choose evaluation measure(s)
Establish baseline data (min 90 days)
Create process for ongoing tracking/monitoring of measure(s)
Education | Establish ongoing ASP education program
Determine needs and establish goals/objectives for program
research available educational resources and outreach opportunities
Create, implement and maintain education program
Action | Implement a policy for documenting dose, duration and indication in E.H.R
Create plan and implement needed tasks to meet this requirement
Reporting |  | Create plan for ongoing tracking and reporting of data to physicians/prescribers
Action | Implement procedure for 48 hour review of appropriateness of antibiotic orders
Create plan and implement needed tasks to meet this requirement
Reporting |  | Create plan for ongoing tracking and reporting of data to physicians/prescribers
Action | Implement one specific intervention for a common infection (community acquired pneumonia, UTI, etc.)
Create plan and implement needed tasks to meet this requirement
Reporting |  | Create plan for ongoing tracking and reporting of data to physicians/prescribers